## Project Timeline
DSLU Shell ECO Marathon
TIMELINE
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE
2016-06-03 | Formal Meeting | 20 | 1
2016-06-10 | Finalization of Task | -10 | 1
2016-07-01 | Start of Task 1 (Modeling of Car Motor and Batteries) | -10 | 1
2016-07-15 | Start of Task 2 (Modeling of Car Motor Controller) | 15 | 1
2016-07-30 | Start of Task 3 (Integration of Models) | -15 | 1
2016-08-15 | Start of Task 4 (Sensors for optimization) | 15 | 1
2016-08-30 | Start of Task 5 (Develop a winning strategy with sensors available) | -15 | 1
2016-09-15 | Optimization/Simulation Task 1 | 20 | 1
2016-09-30 | Optimization/Simulation Task 2 | -15 | 1
2016-11-01 | Registration Period | 15 | 1
2016-12-01 | Completed Car | -20 | 1
2017-01-15 | PH Elimination | 15 | 1
2017-02-15 | Car to be sent to SG | -15 | 1
2017-03-06 | SG Competion Date | 15 | 1
Project Timeline Tips:
The role of the Position values in the Project Details table is to prevent the Milestone labels from overlapping each other on the timeline. Use positive numbers to position labels above the timeline and negative numbers to position them below.
To add additional Milestones, either insert new rows within the table or start typing below the last table entry and the table will automatically expand to accommodate your newly added data.

## Meeting
2016-06-03 | Testing Phase for Motor Controller and Motor
Confirmed commitment for the students to push for the MBD journey
Task to be created in the coming days
PH competition in the beginning of the Year for PH elimination